## Sheet1
Task |  | Data of Beginnig | Task Complet Time | Date of Completion | Task Progress | Design | Problem | Solution | Problem Solute Time
Map Page | 1 |  |  |  | Completed | Completed
[7 empty] | Django query in rast api | rast api serializer and view | 1/2 day
[7 empty] | Django rest api contain data of related with foreign key tabel in one api | used serializer relations consept of django rast framework | 1 day
[7 empty] | Like query in django rast api for search skill,post,etc.. | used search filter of django rast framework | 2 day
[7 empty] | filter data with searched data in api | used search filter with django filter backend | 1/2 day
User Register Page | 2 | 2020-02-28 | 4 day | 2020-03-04 | Completed | Completed
[7 empty] | create post method in react js to parss data to rast api and database | created deffrent json object for each api to send | 1 day
[7 empty] | upload file and image to server | used formData method of react js and used axias instead fetch for post data | 1/2 day
User Login Page | 3 | 2020-03-05 | 4 day | 2020-03-12 | Completed | Completed
[7 empty] | we need two user model jobseeker and emploayer for our site but in django do not allow two user model | we can use django user model for login logout or can creat custom usre model and we can use single model for both jobseeker and emploayer to login and logout | 1 day
[7 empty] | in react js user is authenticeted or login check | react js has property react-redux to haendel login,logout and authenticet user | 1 day
[7 empty] | I was on leave 11/3/2020 |  | 1 day
Recruiter Register Page | 4 | 2020-03-13 | 2 day | 2020-03-16 | On Going | Completed
Recruiter Job Post Page | 5 | 2020-03-17 | 2 day | 2020-03-18 | Not Started | Completed
Recruiter Login Page | 6 | 2020-03-19 | 2day | 2020-03-20 | Not Started | Completed
Company Detail Page | 7 | 2020-03-23 | 4 day | 2020-03-26 | Pendding | Penddind
Finding a distance between uesr and company
Job Detail Page | 8 | 2020-03-27 | 3 day | 2020-03-31 | Not Started | Penddind
Job Seeker Detail Page | 9 | 2020-04-01 | 3 day | 2020-04-03 | Not Started | Penddind
Home Page | 10 | 2020-04-06 | 3 day | 2020-04-08 | Not Started | Penddind